## Risk log
Risk Register
Project name: |  |  | A Personalised Chatbot
Project members: |  |  | Shayan Saebi <22985466> Chukwuebuka Kamsiyochukwu Anwasi <22990144> Zach Patrick Manson <22903345> Yunlong Wei <21805762> Dante Shabani <22868526> Zarhmon Daniel Knipping <22856487>
Team number: |  |  | 41
RISK ID | Risk Name | Date Reported | Description of Risk | Likelihood | Impact | Severity | Risk Manager | Mitigating action | Contingent action | Progress on actions | Status
[1] | Risk Name | [12/12/2015] | [There is a risk that.... If this happens.....] | [High/Medium/Low] | [Extreme/High/Medium/Low] | [High/Medium/Low] | [Person managing the risk] | [Actions that can be taken to reduce the likelihood of the risk occuring. May also be acceptance of the risk or transferance of the risk e.g. insurance] | [What will be done if this risk does occur. Usually actions to reduce the impact on the project] | [Action taken and date. E.g. Update 12/03/2015 mitigation actions implemented] | [Open, Waiting, Closed]
Schedule Risk
1 | Incompletion Risk | [11/08/2022] | There is a risk that the tasks and deliverables requried for Sprint 1 may not be completed in time. | Low | Extreme | High | Project Team | Share the schedule and go through upcoming tasks at each weekly meeting. | Meeting immediately and rescheduling tasks if needed. | Update 11/08/2022 mitigation actions implemented | Open
2 | Unavailability Risk | 2022-08-02 | There is the risk that the various roles external to the group (Project Auditor, Mentor, etc.) are unable to meet at the intended time period, potentially delaying the progression of the project (e.g. the delayed release of the Mentor's causing the first mentor meeting to be pushed back a week). | Medium | Medium | Medium | External Roles | Schedule comfortably in advance to allow adequate time for changes or clashes. | Speak to Unit Co-ordinator if key meetings with external roles aren't able to progress (begins to get detrimental to the project) | Update 12/08/2022 mitigation actions implemented | Open
Technology Risk
| Obsolence | 2022-08-03 | As software continues to be updated/modified theres always the possibility that’s parts of the design solution may soon become obsolete. | Low | Medium | Low | Project Team | Continuously evaluate the necessary usage of every software and resource used throughout the project. Ask ourselves, "will this technology continue to support the client even after we've concluded"?. Discussions with the client and the Team Mentor can help to direct away from resources or technology that may not be sustainable. | Liaise with Client to find best alternatives to minimise any loss of completiton to the Project (considering seeking advise from Mentor) | Update 11/08/2022 mitigation actions implemented | Open
| Compatibility Risk | 2022-08-04
Client Risk
2 | Insufficiency Risk | 2022-08-09 | There is a risk that the Client feels that the requirements established for the design and/or the deliverables provided for the Sprint haven't been sufficiently met. | Low | High | Medium | Project Team + Client | Regular, well-annotated meetings with the client that continuously account for the changing needs of the client and the abilities/scope of the project team. | Immediate meeting to mitigate as many of the clients outstanding requirements. Additionally, reflection to ensure it doesn't happen again. | Update 11/08/2022 mitigation actions implemented | Open
3 | Description Risk | 2022-08-06 | The risk that the client is unable to appropriately describe or explain the requirement that they desire to the project team, leading to a misinterpeted or mismanaged design feature (e.g. Client might suggest a ChatBot with "changing avatar's" when they're actually referring to customisable avatars. | Medium | High | High | Project Team + Client | Regular, well-annotated meetings with the client that continuously account for the changing needs of the client and the abilities/scope of the project team. Additionally, showing the client tangible updates so they're aware of how the product is being developed | Immediate meeting to mitigate and clearly understand what the client desired and if there's sufficient time/resources to account for that. Additionally, reflection to ensure it doesn't happen again. | Update 11/08/2022 mitigation actions implemented | Open
4 | Expectation Risk | 2022-08-11 | There is the risk that the client firmly requires or expects something of the project team that is potentially out of the course's scope, past the team's ability, or is challenged by time and resource limitations. An example of this would be expecting some fairly complex software such as a face recognition sign-in system as a prioritised requirement. | Low | High | Medium | Project Team + Client | A well-done Skills and Resources audit along with a Scope of Work will be helpful in communicating any mismatches in exceptations, skillsets, or goals between the Client and Project Team. | Looks at alternatives or substitute's for the requirement that are more within the scope/abilities of the Project Team (instead of a face recognition system, perhaps a secure PIN-login) | Update 11/08/2022 mitigation actions implemented | Open
Resource Risk
| Resources: Availability & Acessibility | 2022-08-04 | There is a risk that the project team simply doesn't have access to the resources it needs or that they aren't available at this moment in time. This could be software with an out-of-budget price point (e.g. expensive software implementations), data that requires approval/licensing to use or software tools that haven't been made available for general use (e.g. non open-source code). | Low | Low | Low | Project Team | A well-done Skills and Resources audit will be fundamental in conveying which resources are desirable, mandatory and unrequired. From there the Project Team can establish resources it may already have, needs to acquire or doesn't need to worry about. | It will be important to communicate this early on with the Client and look for alternative's or substitute's that will not require the unavailable resource. | Update 11/08/2022 mitigation actions implemented | Open
| Missing Skill Set Risk | 2022-08-06 | There is a possibility that for various reasons the skillset of the team is inadequate/doesn't match with the key requirements needed to succesfully complete the project. This could be due to factors such as the team understimating the project when applying, not having the experience or independence to facilitiate a group, etc. | Low | Extreme | High | Project Team | Thorough research of the project before commencing, a Skills and Resources audit along with a Scope Work should clearly outline what abilities are expected at a base level to succesfully complete the project. This will need to be well communicated between the team and the client. | Since this could have a very early detrimental effect on the project, it would require honesty and determination from the Project Team to communicate this with the client and the Unit Co-ordinator and to discuss a solution. | Update 11/08/2022 mitigation actions implemented | Open
Unforseeable Risk
| COVID-19 | 2022-07-28 | As society continues to adapt with the the ongoing presence COVID-19, a new mutated strain or infecting resurgence is always possible. The potential for delays or shutdowns of in-person meetings or delivery of content reamins vulnerable to this and can compromise the completion of the project | Low | Medium | Medium | Everyone | As an unforeseeable risk, there's notably very little that can be done to prevent or mitigate this from happening apart from encouraging vaccination, good hygeine practices and following expert health advice. | In the possibility that this does happen, we are hopefully experienced enough to implement appropriate measures (online communication, remote learning, visual presentation etc.) | Update 11/08/2022 mitigation actions implemented | Open
| Member Emergency | 2022-07-29 | There is a possibility that a team member is forced to withdraw from the course or can no longer take part in the project (e.g. health and wellbeing emergency, locational challenges, unit discontinuation etc.). If insufficiently accounted for this could have devestating effects on the group;. | Low | High | Medium | Project Team + Unit Coordinator | As an unforeseeable risk, there's notably very little that can be done to prevent or mitigate this from happening. Keeping tabs or informed about members personal wellbeing or personal situations will keep the team best prepared should it happen | If this does happen, meet with Client and Unit Coordinator immediately to discuss how the situation can be handled (reshuffling of tasks/timelines, requirements leniency) | Update 11/08/2022 mitigation actions implemented | Open

## Severity Table
Severity table or Risk Matrix
Likelihood
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Medium
| 2 | Low | Medium | High
| 3 | Medium | High | High
Alternative Severity Tables
4 by 4 Risk Matrix
5 by 5 risk matrix - aviation example

## Useful resources
Risk Management resources
The Top 20 Common project risks with mitigating actions
The Top 50 Business Risks and how to manage them
Key Risks in Construction Projects
Issue Log Template [free download]
How to manage risk on your project